## Sheet1
| Aug. 2011 |  | Sept. 2011 |  |  |  | Oct. 2011 |  |  |  |  | Nov. 2011 |  |  |  | Dec. 2011 |  |  |  | Jan. 2012 |  |  |  | Feb. 2012
Task/Milestone | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
1) Research
Packet Analysation
System-Wide Data Logging
Tri-angulation Mathematics
2) Design
Client Sever Architecture
Spatial Scheme
3) Alpha Hardware/Software
Single Operating and Logging Node
Data Collection
4) Beta/Prototype
Multiple Nodes (2-D Tracking)
Data Processing and Analyzing
Produce Spatial Coordinates
5) Final Prototype
User Interface
Spatial Representation